## Sheet1
Gap Assesment Report: Skybridge Digital
Subcategory | Current | Target | Gap Severity | Recommended Action | Owner | Target Date
GV.OC-03 | Partial | Centralized compliance requirements register | High | Create and maintain a centralized register of legal, regulatory, and contractual requirements. | Compliance Manager | Q4 2026
GV.RM-01 | Partial | Formal risk appetite and tolerance | High | Obtain leadership approval for enterprise cybersecurity risk appetite and tolerance levels. | CISO | Q4 2026
GV.RR-01 | Partial | Clearly documented cybersecurity responsibilities | High | Develop and approve a RACI matrix covering security, IT, cloud, business units, and vendors. | CISO | Q4 2026
GV.PO-01 | Partial | Comprehensive security policy framework | Medium | Review and standardize security policies across cloud, applications, remote work, and third-party environments. | CISO | Q1 2027
GV.OV-01 | Not Implemented | Quarterly cybersecurity strategy review | High | Establish a formal quarterly cybersecurity strategy and risk review process for senior leadership. | CISO | Q4 2026
GV.SC-02 | Partial | Formal third-party risk classification | High | Implement a vendor risk-tiering methodology based on criticality, data access, and business impact. | Third-Party Risk Manager | Q4 2026
ID.AM-01 | Partial | Complete enterprise asset inventory | High | Consolidate asset discovery across offices, remote endpoints, AWS, Azure, and other infrastructure. | IT Asset Manager | Q1 2027
ID.AM-02 | Partial | Centralized software and application inventory | Medium | Establish an authorized software and application inventory with regular reconciliation. | IT Operations Manager | Q1 2027
ID.AM-03 | Partial | Documented critical data flows | High | Map data flows for the payment platform, public-facing applications, cloud environments, and critical vendors. | Data Protection Officer | Q1 2027
ID.RA-01 | Partial | Continuous vulnerability discovery | Critical | Expand vulnerability scanning across cloud infrastructure, endpoints, applications, and internet-facing assets. | Vulnerability Management Lead | Q3 2026
ID.RA-04 | Partial | Standardized enterprise risk scoring | High | Implement a consistent likelihood-and-impact risk scoring methodology. | Enterprise Risk Manager | Q4 2026
ID.RA-05 | Partial | Centralized risk register | High | Implement a centralized risk register with risk owners, treatment plans, deadlines, and acceptance decisions. | Enterprise Risk Manager | Q4 2026
PR.AA-01 | Implemented | Centralized identity lifecycle management | Medium | Integrate all relevant employees, contractors, and third parties into a consistent identity lifecycle process. | IAM Manager | Q4 2026
PR.AA-03 | Partial | Quarterly critical access reviews | High | Establish quarterly reviews for privileged accounts and access to critical systems. | IAM Manager | Q3 2026
PR.AA-05 | Partial | MFA for all critical access | Critical | Enforce MFA across cloud platforms, M365, remote access, privileged accounts, and critical applications. | IAM Manager | Q3 2026
PR.AT-01 | Partial | Mandatory measurable security awareness | Medium | Implement mandatory training with completion tracking and periodic effectiveness testing. | Security Awareness Manager | Q4 2026
PR.DS-01 | Partial | Encryption at rest for sensitive data | High | Establish encryption standards and remediate unencrypted sensitive data stores. | Data Security Manager | Q1 2027
PR.DS-02 | Partial | Strong encryption in transit | High | Standardize encryption requirements for sensitive data transmitted across internal networks and third parties. | Security Architecture Manager | Q4 2026
PR.PS-01 | Partial | Secure configuration baselines | High | Develop and enforce secure configuration baselines for AWS, Azure, M365, endpoints, and servers. | Security Engineering Manager | Q1 2027
PR.PS-04 | Partial | Risk-based patching with SLAs | Critical | Define risk-based patching timelines and monitor remediation against approved SLAs. | Vulnerability Management Lead | Q3 2026
DE.CM-01 | Partial | Centralized network and cloud monitoring | High | Expand security monitoring coverage across AWS, Azure, corporate networks, and critical infrastructure. | SOC Manager | Q4 2026
DE.CM-03 | Partial | Centralized user and administrator monitoring | High | Centralize logging and monitoring of privileged and high-risk user activity. | SOC Manager | Q4 2026
DE.CM-09 | Partial | Continuous cloud and application monitoring | Critical | Implement continuous monitoring for public-facing applications and critical cloud workloads. | Cloud Security Manager | Q3 2026
DE.AE-02 | Partial | Automated cross-environment event correlation | High | Integrate security events from AWS, Azure, M365, endpoints, and applications into centralized analysis. | SOC Manager | Q1 2027
DE.AE-03 | Partial | Centralized security event aggregation | High | Improve centralized collection and retention of security logs from critical systems. | SIEM Manager | Q4 2026
RS.MA-01 | Partial | Tested incident response procedures | Critical | Develop and conduct tabletop exercises for ransomware, cloud compromise, payment platform compromise, and major outages. | Incident Response Manager | Q3 2026
RS.CO-02 | Partial | Standardized incident communications | High | Define communication procedures for executives, customers, regulators, employees, and third parties. | CISO / Communications Director | Q4 2026
RS.AN-03 | Partial | Documented root-cause analysis | Medium | Establish a formal post-incident review and lessons-learned process for significant incidents. | Incident Response Manager | Q4 2026
RS.MI-01 | Partial | Tested containment and eradication playbooks | Critical | Develop and test response playbooks for ransomware, compromised accounts, cloud attacks, and application compromise. | Incident Response Manager | Q3 2026
RC.RP-01 | Partial | Tested recovery procedures | Critical | Conduct regular recovery testing for payment services, critical applications, cloud infrastructure, and M365. | Business Continuity Manager | Q3 2026
RC.CO-02 | Partial | Formal recovery communications | Medium | Establish defined communication responsibilities and escalation paths during service recovery. | Business Continuity Manager | Q4 2026