## Sheet1
Risk Prioritization & Remediation Roadmap : SkyBridge Digital Services
Priority | Risk / Gap | Related CSF | Severity | Recommended Action | Owner | Target
1 | Incomplete MFA coverage | PR.AA-05 | Critical | Enforce MFA for critical systems, cloud platforms, M365, and remote access. | IAM Manager | Q3 2026
2 | Inconsistent vulnerability scanning and patching | ID.RA-01 / PR.PS-04 | Critical | Expand vulnerability scanning and establish patching deadlines based on risk. | IT Security Team | Q3 2026
3 | Limited monitoring of cloud and public-facing applications | DE.CM-09 | Critical | Improve monitoring of AWS, Azure, and internet-facing applications. | Security Operations | Q3 2026
4 | Incident response procedures need testing | RS.MA-01 / RS.MI-01 | High | Test response procedures for major incidents such as ransomware and cloud compromise. | Incident Response Team | Q4 2026
5 | Recovery procedures are not consistently tested | RC.RP-01 | High | Test recovery procedures for critical applications and payment services. | Business Continuity Team | Q4 2026
6 | Incomplete asset inventory | ID.AM-01 | High | Create a complete inventory of important hardware and cloud assets. | IT Operations | Q4 2026
7 | Inconsistent third-party risk assessment | GV.SC-02 | High | Classify critical vendors based on their access, importance, and risk. | Vendor Management | Q4 2026
8 | Inconsistent access reviews | PR.AA-03 | High | Conduct regular reviews of privileged and critical system access. | IAM Manager | Q4 2026