## Sheet3
Evidence Collection Plan
Control ID | Evidence Needed | Source | Frequency | Owner | Jan | Feb | Mar | Apr | May | Jun
C-007 | MFA enrollment and enforcement report | Identity Provider | Monthly | IT Director | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
C-008 | Completed quarterly user access review with management approval | Identity and Access Management System | Quarterly | IT Director | ✓ |  |  |  | ✓
C-009 | Employee termination records and corresponding account disablement evidence | HR / IT Service Desk | Per termination | HR / IT | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
C-010 | Security monitoring review records and relevant security event logs | Security Monitoring Platform | Monthly | Security Lead | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
C-012 | Approved production change tickets with testing and deployment evidence | Change Management / CI-CD Platform | Per production change | Engineering Manager | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
C-014 | Risk treatment and remediation status updates | Risk Register / GRC Tracker | Monthly | GRC Analyst | ✓ | ✓ | ✓ | ✓ | ✓ | ✓

## Sheet1
Gap Analysis: Brightloop
CC/TSC | Requirement | Current State | Gap | Severity | Remediation Plan | Owner | Target Date | Status
CC1.1 | Management demonstrates commitment to integrity and ethical values | No formal SOC 2 compliance program or documented security governance structure exists | Security governance responsibilities and management oversight are not formally documented | High | Approve an Information Security Policy and establish a formal security governance structure | CISO | 2026-08-15 | Open
CC1.2 | The board or management demonstrates independence from management and exercises oversight | Management oversight of security and compliance activities is informal and not documented | No formal management review or oversight process exists for security control effectiveness | Medium | Establish quarterly management review of security risks, controls, and significant findings | CISO | 2026-09-15 | Open
CC1.3 | Management establishes structures, reporting lines, authority, and responsibility | Technical responsibilities exist but control ownership is not formally documented | Control ownership and accountability are not consistently assigned | High | Document control owners and create a Control Ownership Matrix | GRC Analyst | 2026-08-31 | Open
CC2.1 | The entity obtains or generates relevant quality information | Operational security information exists across systems but is not managed as a formal compliance evidence program | Evidence requirements and information ownership are not consistently defined | Medium | Create a control evidence register and define evidence requirements for each control | GRC Analyst | 2026-09-15 | Open
CC2.2 | The entity internally communicates information necessary to support objectives | Employees receive operational communications but formal security policy communication is not consistently documented | No formal process exists to communicate security policies and responsibilities consistently | Medium | Implement policy acknowledgement and documented security awareness communication process | HR / Security Lead | 2026-09-30 | Open
CC2.3 | The entity communicates with external parties regarding matters affecting control functioning | External security and compliance communication processes are not formally documented | Customer and relevant external stakeholder communication responsibilities are not clearly defined | Medium | Document customer security communication and incident notification responsibilities | CISO / Legal | 2026-10-15 | Open
CC3.1 | The entity specifies suitable objectives to enable identification and assessment of risks | No formal enterprise information security risk assessment methodology exists | Risks are not consistently identified and assessed using a documented methodology | High | Implement a formal information security risk assessment methodology and risk register | GRC Analyst | 2026-08-31 | Open
CC3.2 | The entity identifies risks to achieving objectives | No formal risk register or structured risk identification process exists | Information security risks are not consistently documented, scored, or assigned | High | Conduct an initial enterprise security risk assessment and establish a maintained risk register | GRC Analyst | 2026-09-15 | Open
CC3.3 | The entity considers potential fraud in assessing risks | Fraud risk considerations are not formally documented as part of risk assessment activities | Fraud risk is not explicitly evaluated within the organization's risk management process | Medium | Add fraud risk considerations to the annual risk assessment methodology | GRC Analyst | 2026-10-15 | Open
CC3.4 | The entity identifies and assesses changes that could significantly impact the system | Changes to technology and business operations occur, but formal change-related risk assessment is not consistently documented | Material changes are not consistently evaluated for security and control impact | Medium | Implement a material change assessment process linked to change management | CISO / Engineering | 2026-10-31 | Open
CC4.1 | The entity selects, develops, and performs ongoing and separate evaluations | Technical monitoring exists, but formal control effectiveness monitoring is not established | No documented ongoing control monitoring and evaluation program exists | Medium | Establish quarterly control monitoring and annual internal control evaluation activities | GRC Analyst | 2026-10-31 | Open
CC4.2 | The entity evaluates and communicates control deficiencies in a timely manner | Control deficiencies are not managed through a formal compliance issue tracking process | Findings and control deficiencies are not consistently tracked through remediation to closure | Medium | Implement a formal issue and remediation tracking process | CISO / GRC Analyst | 2026-09-30 | Open
CC5.1 | The entity selects and develops control activities that contribute to risk mitigation | Strong technical controls exist, but they are not fully documented in a formal control framework | Existing security activities are not consistently documented with objectives, owners, and evidence requirements | High | Create and maintain a formal SOC 2 control library and control matrix | GRC Analyst | 2026-08-31 | Open
CC5.2 | The entity selects and develops general control activities over technology | Strong technical access controls exist, but supporting technology control documentation is incomplete | Technology controls are not fully documented and mapped to business risks | Medium | Document technology control procedures and map them to relevant SOC 2 criteria | IT Director | 2026-09-30 | Open
CC5.3 | The entity deploys control activities through policies and procedures | Some operational procedures exist but are not consistently formalized or maintained | Control activities are not consistently supported by approved policies and procedures | Medium | Formalize key security policies and operating procedures | CISO | 2026-10-15 | Open
CC6.1 | The entity implements logical access security software, infrastructure, and architectures | Strong technical access controls are already in place | No significant technical gap identified; evidence and control documentation require formalization | Low | Document existing logical access controls and establish recurring evidence collection | IT Director | 2026-08-15 | In Progress
CC6.2 | Prior to issuing system credentials and registering users, the entity registers and authorizes new users | Access provisioning controls exist but formal approval evidence is not consistently retained | User access approval evidence is not consistently documented | Medium | Require documented approval before provisioning access to in-scope systems | IT Director | 2026-08-31 | In Progress
CC6.3 | The entity authorizes, modifies, or removes access based on authorization | Access reviews are performed inconsistently and have no fixed cadence | No formal recurring access review schedule exists | Medium | Establish quarterly access reviews with documented management approval and automated reminders | IT Director | 2026-08-31 | In Progress
CC6.4 | The entity restricts physical access to facilities and protected information assets | Physical security is managed through facilities and cloud provider controls, but responsibility and evidence are not formally documented | Physical security responsibilities and third-party evidence are not formally documented | Low | Document physical security responsibilities and retain relevant AWS and facility evidence | IT Director | 2026-09-30 | Open
CC6.5 | The entity discontinues logical and physical access upon termination | Access removal processes exist but evidence retention and timing are not consistently documented | Termination access removal evidence is not consistently retained | Medium | Formalize offboarding workflow and retain access removal evidence | HR / IT | 2026-08-31 | In Progress
CC6.6 | The entity implements controls against threats outside the system boundaries | AWS security services and network controls exist, but control documentation is incomplete | External threat protection activities are not fully documented as formal controls | Medium | Document network security, monitoring, and external threat protection procedures | IT Director | 2026-09-30 | Open
CC6.7 | The entity restricts transmission, movement, and removal of information | Technical protections exist, but information transfer and data handling requirements are not fully documented | Data transmission and information handling controls are not consistently documented | Medium | Document data handling and transmission security procedures | CISO / IT Director | 2026-10-15 | Open
CC6.8 | The entity implements controls to prevent or detect unauthorized or malicious software | Technical security tooling exists, but evidence and monitoring procedures are not fully formalized | Malware prevention and detection activities lack complete documented evidence requirements | Medium | Document endpoint and malware protection procedures and define evidence collection requirements | IT Director | 2026-10-15 | Open
CC7.1 | The entity detects and monitors for security events | Technical monitoring capabilities exist, but formal monitoring procedures and review evidence are not fully documented | Monitoring activities and review responsibilities are not consistently documented | Medium | Document security monitoring procedures and retain monitoring review evidence | Security Lead | 2026-09-30 | Open
CC7.2 | The entity monitors system components for anomalies indicative of malicious acts | Monitoring exists through technical systems, but anomaly review procedures are not formally documented | Anomaly monitoring responsibilities and escalation procedures are not consistently documented | Medium | Document monitoring and escalation procedures for suspicious activity | Security Lead | 2026-09-30 | Open
CC7.3 | The entity evaluates security events to determine whether they are incidents | No formal documented incident response process exists | Incident classification, escalation, and response procedures are not formally documented | High | Develop and approve a formal Incident Response Plan | CISO | 2026-08-15 | Open
CC7.4 | The entity responds to identified security incidents | Informal response procedures may exist, but no formal tested response process is documented | Incident response responsibilities and procedures have not been formally tested | High | Conduct an incident response tabletop exercise and document lessons learned | CISO | 2026-09-30 | Open
CC7.5 | The entity identifies, develops, and implements activities to recover from identified security incidents | Recovery activities exist through operational processes, but formal incident recovery procedures are not documented | Incident recovery and post-incident improvement activities are not formally defined | Medium | Add recovery, post-incident review, and lessons-learned procedures to the Incident Response Plan | CISO / IT Director | 2026-10-15 | Open
CC8.1 | The entity authorizes, designs, develops, configures, documents, tests, approves, and implements changes | Development and deployment processes exist, but formal change approval and evidence requirements are not consistently documented | Production changes may not consistently have complete approval, testing, and deployment evidence | Medium | Implement formal change management procedures for production changes | Engineering Manager | 2026-09-15 | Open
CC9.1 | The entity identifies, selects, and develops risk mitigation activities | Some risks are managed operationally, but there is no formal risk treatment process | Risk treatment decisions and mitigation activities are not consistently documented | High | Implement a formal risk treatment and remediation tracking process | GRC Analyst | 2026-09-30 | Open
CC9.2 | The entity assesses and manages risks associated with vendors and business partners | No formal vendor risk program exists | Third-party vendors are not consistently classified, assessed, or monitored | High | Implement vendor inventory, risk tiering, security assessment, and periodic review process | GRC Analyst | 2026-09-15 | Open

## Sheet2
Control Matrix : Brightloop
Control ID | Control Description | CC/TSC Reference | Owner | Evidence Type | Status
C-001 | Information Security Policy is approved by management and reviewed at least annually | CC1.1 | CISO | Approved policy document; annual review record | In Progress
C-002 | Security responsibilities and control ownership are formally assigned | CC1.3 | GRC Analyst | Control Ownership Matrix; responsibility assignments | In Progress
C-003 | Employees complete security awareness training and acknowledge applicable security policies | CC2.2 | HR / Security Lead | Training completion report; policy acknowledgement records | In Progress
C-004 | Information security risks are formally identified, assessed, and recorded in a risk register | CC3.1; CC3.2 | GRC Analyst | Risk assessment; risk register | In Progress
C-005 | Management reviews security risks, control performance, and significant deficiencies periodically | CC4.1; CC4.2 | CISO | Management review minutes; action tracker | Open
C-006 | Security controls are documented with defined owners, procedures, and evidence requirements | CC5.1 | GRC Analyst | Control library; control matrix | In Progress
C-007 | MFA is enforced for privileged and applicable user accounts | CC6.1 | IT Director | Identity provider configuration export; MFA report | Implemented
C-008 | User access to in-scope systems is reviewed and approved quarterly | CC6.3 | IT Director | Completed access review tracker; approval records | In Progress
C-009 | Access is removed promptly when personnel leave the organization | CC6.5 | HR / IT | Termination ticket; account disablement record | In Progress
C-010 | Security events are monitored and evaluated for potential incidents | CC7.1; CC7.2 | Security Lead | Security monitoring logs; review records | Implemented
C-011 | Security incidents are classified, escalated, and handled according to a documented Incident Response Plan | CC7.3; CC7.4 | CISO | Approved IR Plan; incident records; tabletop exercise report | Open
C-012 | Production changes require documented authorization, testing, and deployment evidence | CC8.1 | Engineering Manager | Change tickets; approvals; test results; deployment records | In Progress
C-013 | Vendors are inventoried, risk-tiered, assessed, and periodically reviewed | CC9.2 | GRC Analyst | Vendor inventory; risk assessments; SOC reports; review records | Open
C-014 | Security risks are treated through documented remediation plans and tracked to completion | CC9.1 | GRC Analyst | Risk treatment plan; remediation tracker | In Progress
C-015 | Physical and cloud infrastructure security responsibilities are documented and supported by relevant third-party evidence | CC6.4 | IT Director | AWS assurance reports; facility security evidence | Open